## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US-01 | Setup project structure and Development environment | MUST HAVE | NA | Desam Surekha | 3- Completed
Sprint 1 | Sprint 1 | US-02 | Understand OOP concepts in java and practice jdbc CRUD operations | SHOULD HAVE | NA | Desam Surekha | 3- Completed
Sprint 1 | Sprint 1 | US-03 | Design Account model and repository | MUST HAVE | US-02 | Desam Surekha | 3- Completed
Sprint 2 | Sprint 2 | US-04 | Implement account creation API | MUST HAVE | US-03 | Desam Surekha | 3- Completed
Sprint 2 | Sprint 2 | US-05 | Implement get account by ID API | MUST HAVE | US-04 | Desam Surekha | 3- Completed
Sprint 2 | Sprint 2 | US-06 | Implement list all accounts API | SHOULD HAVE | US-04 | Desam Surekha | 3- Completed
Sprint 3 | Sprint 3 | US-07 | Implement deposit functionality | MUST HAVE | US-03 | Desam Surekha | 3- Completed
Sprint 3 | Sprint 3 | US-08 | Implement withdrawal functionality | MUST HAVE | US-07 | Desam Surekha | 3- Completed
Sprint 3 | Sprint 3 | US-09 | Implement transfer functionality | MUST HAVE | US-07 | Desam Surekha | 3- Completed
Sprint 3 | Sprint 3 | US-10 | Add transaction validations | MUST HAVE | US-08 | Desam Surekha | 3- Completed
Sprint 4 | Sprint 4 | US-11 | Implement balance alert service | SHOULD HAVE | US-08 | Desam Surekha | 3- Completed
Sprint 4 | Sprint 4 | US-12 | Service layer Unit Testing | MUST HAVE | US-10 | Desam Surekha | 3- Completed
Sprint 4 | Sprint 4 | US-13 | Backend Integration | MUST HAVE | US-12 | Desam Surekha | 3- Completed
Sprint 5 | Sprint 5 | US-14 | Develop frontend UI- HTML Structure | SHOULD HAVE | NA | Desam Surekha | 3- Completed
Sprint 5 | Sprint 5 | US-15 | Add java Script to the pages | MUST HAVE | US-14 | Desam Surekha | 3- Completed
Sprint 5 | Sprint 5 | US-16 | Add Stylings -CSS to the HTML | MUST HAVE | US-14 | Desam Surekha | 3- Completed
Sprint 6 | Sprint 6 | US-17 | Integrate Front End with Backend APIs | MUST HAVE | US-15 | Desam Surekha | 3- Completed
Sprint 6 | Sprint 6 | US-18 | Perform end to End testing | MUST HAVE | US-17 | Desam Surekha | 3- Completed
Sprint 6 | Sprint 6 | US-19 | Deploy the Frontend and Backend and perform final testing | SHOULD HAVE | US-19 | Desam Surekha | 2- In Progress
Note on F1: ====== ID#AAAB26msPaU Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 54 | 27 | 19 | 7 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-01 | 1 | Introduction to Project(Banking Activity Simulation) | 2026-02-16 | 2026-02-16 | Desam Surekha | Knowledge Transfer | Completed | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-02 | 2 | Discussion on java basics and jdbc CRUD operations | 2026-02-17 | 2026-02-17 | Desam Surekha | Tech Training | Completed | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-03 | 3 | Document Discussion | 2026-02-18 | 2026-02-22 | Desam Surekha | Analysis | Completed | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 2- BACKLOG
US-04 | 4 | System model design and architectural discussion | 2026-02-23 | 2026-02-25 | Desam Surekha | System Design | Completed | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-05 | 5 | Implementation of getAccountById and logic review | 2026-02-26 | 2026-02-28 | Desam Surekha | Backend Dev | Completed | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-06 | 6 | Error handling and code review for Account modules | 2026-03-01 | 2026-03-03 | Desam Surekha | Error handling | Completed | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 3- BACKLOG
US-07 | 7 | Backend workflow analysis and debugging | 2026-03-04 | 2026-03-07 | Desam Surekha | Debugging | Completed | 5 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-08 | 8 | Development and completion of Repository methods | 2026-03-08 | 2026-03-12 | Desam Surekha | Backend Dev | Completed | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-09 | 9 | Implementation of balance alert service | 2026-03-13 | 2026-03-15 | Desam Surekha | Coding | Completed | 4 | 1 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-10 | 10 | Extended testing for repository methods | 2026-03-16 | 2026-03-16 | Desam Surekha | Testing | Completed | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 4- BACKLOG
US-11 | 11 | Alert module and email library integration | 2026-03-17 | 2026-03-18 | Desam Surekha | Coding | Completed | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-12 | 12 | Unit testing on service layer | 2026-03-17 | 2026-03-19 | Desam Surekha | Testing | Completed | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-13 | 13 | Module integration review | 2026-03-17 | 2026-03-18 | Desam Surekha | Integration | Completed | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 5- BACKLOG
US-14 | 14 | Develop frontend UI-HTML structure | 2026-03-19 | 2026-03-22 | Desam Surekha | Coding | Completed | 5 | 3 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-15 | 15 | Add java script to the pages | 2026-03-23 | 2026-03-27 | Desam Surekha | Coding | Completed | 4 | 1 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-16 | 16 | Add stylings -CSS to the HTML | 2026-03-28 | 2026-03-31 | Desam Surekha | Coding | Completed | 6 | 2 | 1 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 6- BACKLOG
US-17 | 17 | Integrate Front end with backend API's | 2026-04-01 | 2026-04-02 | Desam Surekha | API integration | Completed | 3 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-18 | 18 | Perform end to end testing | 2026-04-01 | 2026-04-02 | Desam Surekha | Quality Assurance | Completed | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-19 | 19 | Deploy the frontend and backend final testing | 2026-04-01 | 2026-04-02 | Desam Surekha | Deployment | In Progress | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on D2: ====== ID#AAAB26msPbI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAAB26msPac Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAAB26msPag Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAAB26msPbM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAAB26msPas Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAAB26msPaQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAAB26msPak Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAAB26msPaI Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAAB26msPbA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAAB26msPbE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAAB26msPa0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAAB26msPaw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAAB26msPaM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAAB26msPao Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAAB26msPa8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAAB26msPaY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAAB26msPa4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 1 | Confusion about the project and its implementation | Clarified by the mentor about project and its requierments
Sprint 1 | Day 3 | Doubts regarding project setup and eclipse version download | Constanly attended the classes to know about the setup and praticed programs earlier before starting the project
Sprint 2 | Day 10 | Difficulty in designing the model | Discussed with the mentor and designed the model
Sprint 2 | Day 16 | Encountered with an error at implementation of get account by ID | Reviewed and solved the error
Sprint 3 | Day 20 | Difficulty in debugging backend code | Attended classes and got to know the workflow
Sprint 3 | Day 27 | Delay in Completing repository methods | Extended work hours and completed
Sprint 4 | Day 30 | Alert module not working and did not got any emails | impoerted the requierd libraries to implement
Sprint 4 | Day 34 | Some modules were not working while unit testing | Reviewed the integration among modules and reconducted testing
Sprint 5 | Day 40 | UI alignment problems | Adjusted using CSS
Sprint 6 | Day 44 | Integration of frontend and backend errors | Performed testing and fixed bugs

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2026-02-16 | 2026-02-22 | Desam Surekha | Clarify project requirements and setup with mentor before starting | Directly starting the project | Attending classes to get more knowledge on java | Practicing
2 | Sprint 2 | 2026-02-23 | 2026-03-03 | Desam Surekha | Implementation of Acoount module | implementing without verifying the design | reviewing and debugging errors collaboratively | Discussed model design with mentor
3 | Sprint 3 | 2026-03-04 | 2026-03-16 | Desam Surekha | Attend debugging sessions and plan time for repository | Delaying repository methods until last moment | Attending classes to understand backend flow | Attended classes and extended work hours
4 | Sprint 4 | 2026-03-17 | 2026-03-19 | Desam Surekha | Import and verify required libraries | Skipping Library checks before module implementation | Reviewing integration before testing | Imported libraries and reviewed module integration
5 | Sprint 5 | 2026-03-20 | 2026-03-31 | Desam Surekha | Check UI alignment components early | Leaving UI alignment issues unaddressed | Using CSS for layout and alignment fixing | Fixed UI alignment using CSS adjustments
6 | Sprint 6 | 2026-04-01 | 2026-04-02 | Desam Surekha | perform integration testing between frontend and backend | Defering integration testing to the end of the sprint | Systematic bug fixing through testing | Performed end to end testing